## Overview
Vakil.app — build tracker
Single-entity case manager for advocates · Expo + NativeWind · Node.js API · Supabase · Plus Jakarta Sans · Tabler icons
Track | Total | Done | In progress | Blocked | % done
Screens: design | 50 | 1 | 0 | 0 | 2%
Screens: development | 50 | 0 | 1 | 0 | 0%
Components: Figma | 56 | 0 | 0 | 0 | 0%
Components: code | 56 | 0 | 0 | 0 | 0%
Requirements: dev | 74 | 0 | 0 | 0 | 0%
Requirements: QA | 74 | 0 | 0 | 0 | 0%
API endpoints: dev | 46 | 0 | 0 | 0 | 0%
Database: migrations | 35 | 0 | 0 | 0 | 0%
How to use
• Update the yellow status columns on each tab using the dropdown (Not started, In progress, In review, Done, Blocked).
• This Overview recalculates automatically from those columns.
• Screens row SCR-01 has example values to show the expected format; reset it when you start.
• Source of truth for detail: the PRD, FRS and User Flow docs.

## Screens
Screen inventory
50 screens, sheets and dialogs. Yellow columns are yours to update (pick from the dropdown).
ID | Screen | Type | Module | Key components | Priority | Design status | Dev status | Notes
SCR-01 | Splash | Screen | Auth | Logo on grad-glow | P0 | Done | In progress | Example row: logo exported
SCR-02 | Welcome carousel (3 slides) | Screen | Onboarding | Illustration, dots, Gradient button | P0 | Not started | Not started
SCR-03 | Sign in (phone) | Screen | Auth | Phone input, Primary button, email link | P0 | Not started | Not started
SCR-04 | Sign in (email + password) | Screen | Auth | Text fields, Primary button | P0 | Not started | Not started
SCR-05 | OTP verification | Screen | Auth | OTP input, 30 s resend timer | P0 | Not started | Not started
SCR-06 | Profile setup | Screen | Onboarding | Avatar, name, enrolment no., practice areas | P0 | Not started | Not started
SCR-07 | Primary courts setup | Screen | Onboarding | Searchable multi-select, Add court | P0 | Not started | Not started
SCR-08 | Notification permission | Screen | Onboarding | Illustration, Allow / Later | P0 | Not started | Not started
SCR-09 | Home dashboard | Tab | Dashboard | Hero card, stat grid, week strip, today list, quick actions | P0 | Not started | Not started
SCR-10 | Today's hearings | Screen | Dashboard | Grouped by court, hearing cards, Update | P0 | Not started | Not started
SCR-11 | Cases list | Tab | Cases | Search, filter chips, sort, case cards, FAB | P0 | Not started | Not started
SCR-12 | Case filters | Sheet | Cases | Status, type, court, date range, client | P0 | Not started | Not started
SCR-13 | Sort options | Sheet | Cases | Radio list | P0 | Not started | Not started
SCR-14 | Add case: 1 Basics | Modal | Cases | Stepper, title, case no., year, type, CNR | P0 | Not started | Not started
SCR-15 | Add case: 2 Court | Modal | Cases | Court select, room, judge, filing date | P0 | Not started | Not started
SCR-16 | Add case: 3 Parties and client | Modal | Cases | Segmented our side, client select/add, parties | P0 | Not started | Not started
SCR-17 | Add case: 4 Stage and next date | Modal | Cases | Stage, next date + quick chips, purpose, priority | P0 | Not started | Not started
SCR-18 | Add case: Review and save | Modal | Cases | Summary cards, Save, Save and add another | P0 | Not started | Not started
SCR-19 | Case detail: Overview | Screen | Cases | Header, status pill, next-date card, info, client card | P0 | Not started | Not started
SCR-20 | Case detail: Hearings | Tab | Hearings | Timeline, Add hearing | P0 | Not started | Not started
SCR-21 | Case detail: Documents | Tab | Documents | Document tiles, upload | P1 | Not started | Not started
SCR-22 | Case detail: Notes | Tab | Notes | Note cards, add note | P1 | Not started | Not started
SCR-23 | Case detail: Fees | Tab | Fees | Fee summary card, payments | P1 | Not started | Not started
SCR-24 | Case detail: Tasks | Tab | Tasks | Checklist rows, add task | P1 | Not started | Not started
SCR-25 | Edit case | Modal | Cases | All case fields, single scroll | P0 | Not started | Not started
SCR-26 | Change status | Sheet | Cases | Status radios, disposal date + result | P0 | Not started | Not started
SCR-27 | Case actions menu | Action sheet | Cases | Edit, status, share, archive, delete | P0 | Not started | Not started
SCR-28 | Delete case confirm | Dialog | Cases | Destructive dialog, type case no. | P0 | Not started | Not started
SCR-29 | Update hearing outcome | Sheet (90%) | Hearings | Outcome chips, notes, next date chips | P0 | Not started | Not started
SCR-30 | Add / edit hearing | Sheet | Hearings | Date, time, purpose, room | P0 | Not started | Not started
SCR-31 | Calendar: month | Tab | Calendar | Month grid with dots, day list | P0 | Not started | Not started
SCR-32 | Calendar: day agenda | Screen | Calendar | Hearing cards by court | P0 | Not started | Not started
SCR-33 | Clients list | Tab | Clients | Search, client cards, FAB | P0 | Not started | Not started
SCR-34 | Add / edit client | Modal | Clients | Name, phone, alt phone, email, address, notes | P0 | Not started | Not started
SCR-35 | Client detail | Screen | Clients | Contact actions, linked cases | P0 | Not started | Not started
SCR-36 | Upload document | Sheet | Documents | Camera / gallery / files, name, category | P1 | Not started | Not started
SCR-37 | Document viewer | Screen | Documents | PDF/image viewer, share, rename, delete | P1 | Not started | Not started
SCR-38 | Add / edit note | Modal | Notes | Title, body, pin toggle | P1 | Not started | Not started
SCR-39 | Add payment / set fee | Sheet | Fees | Amount, date, mode, note | P1 | Not started | Not started
SCR-40 | Global search | Screen | Search | Search bar, recent, grouped results | P1 | Not started | Not started
SCR-41 | Notifications centre | Screen | Notifications | Rows grouped by day, mark all read | P0 | Not started | Not started
SCR-42 | More / Profile hub | Tab | Settings | Profile header, settings rows | P0 | Not started | Not started
SCR-43 | Edit profile | Modal | Settings | Profile fields | P0 | Not started | Not started
SCR-44 | Appearance | Screen | Settings | Dark / Light / System segmented, preview | P0 | Not started | Not started
SCR-45 | Notification settings | Screen | Settings | Toggles + time pickers | P0 | Not started | Not started
SCR-46 | Manage courts and case types | Screen | Settings | Editable lists, reorder | P0 | Not started | Not started
SCR-47 | Security (app lock) | Screen | Settings | Biometric toggle, PIN | P1 | Not started | Not started
SCR-48 | Help and about | Screen | Settings | FAQ, contact, version, privacy | P0 | Not started | Not started
SCR-49 | Logout / delete account | Dialog | Settings | Confirm dialogs | P0 | Not started | Not started
SCR-50 | System states | Overlay | Global | Offline banner, error, empty, force update | P0 | Not started | Not started

## Components
UI component library
56 components. States for all: default, pressed (0.97), focused, disabled (40%), loading; inputs add error. Dark + light.
ID | Group | Component | Variants | Size (dp) | Style notes | Figma status | Code status
CMP-01 | Actions | Button | Primary, Gradient, Secondary, Outline, Ghost, Destructive, Destructive-ghost | sm 36, md 44, lg 52 | rounded-md, button type, icon 20, loading spinner | Not started | Not started
CMP-02 | Actions | Icon button | Filled, Tonal, Ghost, Outline | 32 / 40 / 48 (target 48) | rounded-md or full | Not started | Not started
CMP-03 | Actions | FAB | Circular, Extended, Speed-dial | 56 / 52 | grad-primary, glow, hide on scroll down | Not started | Not started
CMP-04 | Actions | Link / text action | Default, Inline, With chevron | 20 line | primary text | Not started | Not started
CMP-05 | Actions | Quick action tile | Icon + label | 88 x 88 | surface card, 40 dp primary-subtle icon circle | Not started | Not started
CMP-06 | Actions | Swipe actions | Leading, Trailing | row height | 72 dp action width, haptic | Not started | Not started
CMP-07 | Inputs | Text field | Filled, Outline; icons, prefix, suffix | 52 | surface-2 fill, label above, helper/error below | Not started | Not started
CMP-08 | Inputs | Text area | Auto-grow 3-10 lines | min 104 | same as field | Not started | Not started
CMP-09 | Inputs | Search bar | Inline, Expanded, With filter | 44 | rounded-full, 300 ms debounce | Not started | Not started
CMP-10 | Inputs | Select (picker) | Bottom-sheet list, searchable, Add new row | 52 | chevron-down trailing | Not started | Not started
CMP-11 | Inputs | Multi-select | Chips in field, checkbox sheet | 52+ | wrap 2 lines then +N | Not started | Not started
CMP-12 | Inputs | Date picker | Calendar sheet + quick chips | 52 | DD MMM YYYY, ddd | Not started | Not started
CMP-13 | Inputs | Time picker | Wheel | - | 12-hour, 15-min steps | Not started | Not started
CMP-14 | Inputs | Phone input | +91 prefix, mask | 52 | numeric keypad | Not started | Not started
CMP-15 | Inputs | OTP input | 6 boxes, autofill | 48 x 56 boxes | shake on error | Not started | Not started
CMP-16 | Inputs | Amount input | INR prefix, Indian grouping | 52 | tabular numbers | Not started | Not started
CMP-17 | Inputs | Stepper form header | Step x of 4 + progress | - | grad-primary progress | Not started | Not started
CMP-18 | Selection | Toggle switch | On / off, label row | 52 x 32 | on = primary | Not started | Not started
CMP-19 | Selection | Checkbox | Unchecked, checked, indeterminate | 22 | rounded-sm | Not started | Not started
CMP-20 | Selection | Radio | Unselected, selected | 22 | 8 dp dot | Not started | Not started
CMP-21 | Selection | Segmented control | 2-4 segments | 40 | sliding pill indicator | Not started | Not started
CMP-22 | Selection | Filter chip | Unselected, selected, with count | 32 | selected = primary-subtle + primary border | Not started | Not started
CMP-23 | Selection | Choice chip | Single-select row | 32 | same as filter chip | Not started | Not started
CMP-24 | Selection | Input chip | Removable, with avatar | 28 | - | Not started | Not started
CMP-25 | Display | Status pill | Active, Today, Adjourned, Reserved, Overdue, Disposed, Closed | 22 / 26 | status subtle bg + text, dot or icon | Not started | Not started
CMP-26 | Display | Badge | Count, Dot, Text | 18 min | rounded-full | Not started | Not started
CMP-27 | Display | Avatar | Initials, Image, Icon | 24/32/40/56/80 | advocate avatar has gradient ring | Not started | Not started
CMP-28 | Display | List row | 1, 2, 3-line; leading/trailing slots | min 56 | divider inset 56 | Not started | Not started
CMP-29 | Display | Section header | Overline + action | - | overline text-3 | Not started | Not started
CMP-30 | Display | Key-value row | Plain, copyable | - | copy icon | Not started | Not started
CMP-31 | Display | Timeline | Past, today, future nodes | - | dot colored by outcome | Not started | Not started
CMP-32 | Display | Calendar month grid | Dots, today ring, selected | 44 cells | max 3 dots | Not started | Not started
CMP-33 | Display | Week strip | 7-day scroller with counts | 56 x 72 | selected = grad-primary | Not started | Not started
CMP-34 | Display | Progress | Linear, Ring, Indeterminate | 6 track | rounded-full | Not started | Not started
CMP-35 | Display | Divider | Full, Inset, With label | 1 | border token | Not started | Not started
CMP-36 | Display | Info tag | Icon + meta text | - | body-sm text-2 | Not started | Not started
CMP-37 | Cards | Hero Today card | Hearings today / none | - | grad-hero, rounded-xl, glow | Not started | Not started
CMP-38 | Cards | Stat card | Icon, number, label, trend | - | 2 x 2 grid, taps filter list | Not started | Not started
CMP-39 | Cards | Case card | Default, Overdue, Archived | - | overdue = 3 dp error left accent | Not started | Not started
CMP-40 | Cards | Hearing card | Upcoming, Needs update, Done | - | Update button | Not started | Not started
CMP-41 | Cards | Client card | With call / WhatsApp | - | - | Not started | Not started
CMP-42 | Cards | Document tile | Grid, List | - | file-type icon, overflow menu | Not started | Not started
CMP-43 | Cards | Note card | Default, Pinned | - | pinned = primary-subtle | Not started | Not started
CMP-44 | Cards | Fee summary card | Balance due, Fully paid | - | ring progress, grad-success when paid | Not started | Not started
CMP-45 | Navigation | Bottom tab bar | 5 tabs | 64 + inset | blur, active filled icon + pill | Not started | Not started
CMP-46 | Navigation | Top app bar | Large, Compact, Transparent, Search | 96 / 56 | large title collapses | Not started | Not started
CMP-47 | Navigation | Tabs | Underline, Pill | 44 | sliding indicator 200 ms | Not started | Not started
CMP-48 | Feedback | Toast / snackbar | Success, Error, Info, With Undo | - | auto-dismiss 4 s (Undo 5 s) | Not started | Not started
CMP-49 | Feedback | Inline banner | Info, Warning, Error, Offline | - | status subtle bg | Not started | Not started
CMP-50 | Feedback | Empty state | Per module | - | icon badge with glow, CTA | Not started | Not started
CMP-51 | Feedback | Skeleton | Card, row, text, avatar | - | grad-shimmer 1.2 s | Not started | Not started
CMP-52 | Overlays | Bottom sheet | Auto, Snap 50/90%, Full | - | rounded-2xl top, scrim | Not started | Not started
CMP-53 | Overlays | Dialog | Confirm, Destructive, Info | max w 340 | rounded-2xl | Not started | Not started
CMP-54 | Overlays | Action sheet | Actions + Cancel | - | - | Not started | Not started
CMP-55 | Overlays | Pull-to-refresh | Native | - | primary tint | Not started | Not started
CMP-56 | Overlays | Loading overlay | Blocking spinner | - | rare | Not started | Not started

## Requirements
Functional requirements
Full detail in the FRS doc. Track build and QA here.
ID | Module | Requirement | Acceptance criteria | Priority | Dev status | QA status | Notes
FR-AUTH-01 | Auth | Sign in with mobile + 6-digit OTP | OTP within 10 s; resend after 30 s; 5 attempts / 15 min | P0 | Not started | Not started
FR-AUTH-02 | Auth | Email + password fallback | Min 8 chars; forgot password link | P0 | Not started | Not started
FR-AUTH-03 | Auth | Persistent session, silent refresh | 30 days; tokens in SecureStore | P0 | Not started | Not started
FR-AUTH-04 | Auth | Route new users to onboarding | Based on onboarded_at | P0 | Not started | Not started
FR-AUTH-05 | Auth | Logout clears tokens, cache, push token | No data reachable after logout | P0 | Not started | Not started
FR-ONB-01 | Onboarding | Profile: name, enrolment no., practice areas, photo | Continue disabled until name valid | P0 | Not started | Not started
FR-ONB-02 | Onboarding | Pick primary courts or add custom | At least 1 court | P0 | Not started | Not started
FR-ONB-03 | Onboarding | Explain then request notification permission | Denied shows banner in Settings | P0 | Not started | Not started
FR-DASH-01 | Dashboard | Hero card with today's hearings | Zero state variant | P0 | Not started | Not started
FR-DASH-02 | Dashboard | Stats: Active, Today, This week, Overdue | Tap opens filtered list | P0 | Not started | Not started
FR-DASH-03 | Dashboard | Week strip with counts | Select day shows hearings | P0 | Not started | Not started
FR-DASH-04 | Dashboard | Quick actions | Open correct flows | P0 | Not started | Not started
FR-DASH-05 | Dashboard | Pull to refresh, cached data | Instant from cache under 60 s | P0 | Not started | Not started
FR-CASE-01 | Cases | 4-step add case form + review | Draft auto-saved | P0 | Not started | Not started
FR-CASE-02 | Cases | Required: title/parties, type, court, side, client | Inline validation on blur | P0 | Not started | Not started
FR-CASE-03 | Cases | Optional fields incl. CNR | CNR = 16 alphanumeric | P0 | Not started | Not started
FR-CASE-04 | Cases | Next date at creation | Creates first hearing; past date warns | P0 | Not started | Not started
FR-CASE-05 | Cases | Auto title 'Petitioner v. Respondent' | Editable | P0 | Not started | Not started
FR-CASE-06 | Cases | Save and add another | Keeps court and type | P0 | Not started | Not started
FR-CASE-07 | Cases | Infinite list sorted by next date | Overdue pinned on top | P0 | Not started | Not started
FR-CASE-08 | Cases | Search title, no., CNR, party, client, court | Under 500 ms | P0 | Not started | Not started
FR-CASE-09 | Cases | Combinable filters | Count on filter button, Clear all | P0 | Not started | Not started
FR-CASE-10 | Cases | Sort options | Persisted per device | P0 | Not started | Not started
FR-CASE-11 | Cases | Case detail | Cache first, then refresh | P0 | Not started | Not started
FR-CASE-12 | Cases | Call / WhatsApp client, copy numbers | wa.me deep link | P0 | Not started | Not started
FR-CASE-13 | Cases | Change status | Disposed requires date + result | P0 | Not started | Not started
FR-CASE-14 | Cases | Archive / restore | archived_at flag | P0 | Not started | Not started
FR-CASE-15 | Cases | Delete with typed confirmation | Soft delete 30 days | P0 | Not started | Not started
FR-CASE-16 | Cases | Share case summary | Native share sheet | P0 | Not started | Not started
FR-HEAR-01 | Hearings | Add hearing | Updates next_hearing_at | P0 | Not started | Not started
FR-HEAR-02 | Hearings | Update outcome from 3 entry points | Sheet pre-filled | P0 | Not started | Not started
FR-HEAR-03 | Hearings | Outcome chips + notes | One tap select | P0 | Not started | Not started
FR-HEAR-04 | Hearings | Next date with quick chips | Atomic API call | P0 | Not started | Not started
FR-HEAR-05 | Hearings | Disposed outcome prompts status change | Opens SCR-26 | P0 | Not started | Not started
FR-HEAR-06 | Hearings | Hearing timeline | Newest on top, Today marker | P0 | Not started | Not started
FR-HEAR-07 | Hearings | Needs update flag | Dashboard warning banner | P0 | Not started | Not started
FR-CLI-01 | Clients | Add client | Duplicate phone warning | P0 | Not started | Not started
FR-CLI-02 | Clients | Inline create from add case | Returns selected | P0 | Not started | Not started
FR-CLI-03 | Clients | Many-to-many cases and clients | case_clients table | P0 | Not started | Not started
FR-CLI-04 | Clients | Client detail with linked cases | Tap opens case | P0 | Not started | Not started
FR-CLI-05 | Clients | Call, WhatsApp, SMS | Device intents | P0 | Not started | Not started
FR-CLI-06 | Clients | Delete only without active cases | Explains why if blocked | P0 | Not started | Not started
FR-CAL-01 | Calendar | Month grid with dots | Fetch by visible month | P0 | Not started | Not started
FR-CAL-02 | Calendar | Day list grouped by court | Empty state | P0 | Not started | Not started
FR-CAL-03 | Calendar | Today button, swipe months | 200 ms transition | P0 | Not started | Not started
FR-NOTIF-01 | Notifications | Evening digest 8 PM day before | Configurable, only if count > 0 | P0 | Not started | Not started
FR-NOTIF-02 | Notifications | Morning digest 8 AM | Configurable | P0 | Not started | Not started
FR-NOTIF-03 | Notifications | 6 PM needs-update nudge | Deep-links to Today | P0 | Not started | Not started
FR-NOTIF-04 | Notifications | Deep links from cold start | Correct screen | P0 | Not started | Not started
FR-NOTIF-05 | Notifications | In-app centre, 60 days | Unread badge | P0 | Not started | Not started
FR-SET-01 | Settings | Edit profile | PATCH /me | P0 | Not started | Not started
FR-SET-02 | Settings | Theme Dark / Light / System | Instant, no restart | P0 | Not started | Not started
FR-SET-03 | Settings | Manage courts and case types | Hidden kept on old cases | P0 | Not started | Not started
FR-SET-04 | Settings | Notification preferences | Saved to profile | P0 | Not started | Not started
FR-SET-05 | Settings | Delete account | Purged within 30 days | P0 | Not started | Not started
FR-DOC-01 | Documents | Upload PDF/images up to 20 MB | Signed URL, progress | P1 | Not started | Not started
FR-DOC-02 | Documents | Categories | Filter chips | P1 | Not started | Not started
FR-DOC-03 | Documents | Preview, rename, share, delete | Pinch zoom | P1 | Not started | Not started
FR-DOC-04 | Documents | Compress images | Max 2000 px | P1 | Not started | Not started
FR-DOC-05 | Documents | 1 GB quota | Usage bar | P1 | Not started | Not started
FR-NOTE-01 | Notes | Add note | Auto-save 2 s | P1 | Not started | Not started
FR-NOTE-02 | Notes | Pin up to 3 | Pinned on top | P1 | Not started | Not started
FR-NOTE-03 | Notes | Edit, delete with Undo | 5 s Undo | P1 | Not started | Not started
FR-NOTE-04 | Notes | Searchable | In global search | P1 | Not started | Not started
FR-FEE-01 | Fees | Agreed fee per case | INR | P1 | Not started | Not started
FR-FEE-02 | Fees | Record payments | Balance = agreed - paid | P1 | Not started | Not started
FR-FEE-03 | Fees | Fee summary ring | grad-success when paid | P1 | Not started | Not started
FR-FEE-04 | Fees | Fees pending stat | Optional | P1 | Not started | Not started
FR-TASK-01 | Tasks | Add task | Optional case link | P1 | Not started | Not started
FR-TASK-02 | Tasks | Check off | Haptic + strike | P1 | Not started | Not started
FR-TASK-03 | Tasks | Overdue in red | - | P1 | Not started | Not started
FR-TASK-04 | Tasks | Due tasks in morning digest | - | P1 | Not started | Not started
FR-SRCH-01 | Search | Global search | 10 recent searches | P1 | Not started | Not started
FR-SEC-01 | Security | Biometric / PIN lock | Lock after 1 min background | P1 | Not started | Not started

## API
REST API endpoints
Base URL https://api.vakil.app/api/v1 · Bearer = Supabase access token verified by the Node API
Method | Endpoint | Purpose | FR ref | Auth (Bearer) | Dev status | Tested
POST | /auth/otp/send | Send OTP | FR-AUTH-01 | No | Not started | Not started
POST | /auth/otp/verify | Verify OTP, return session | FR-AUTH-01 | No | Not started | Not started
POST | /auth/email/sign-in | Email sign-in | FR-AUTH-02 | No | Not started | Not started
POST | /auth/refresh | Refresh token | FR-AUTH-03 | No | Not started | Not started
POST | /auth/logout | Logout | FR-AUTH-05 | Yes | Not started | Not started
GET | /me | Get profile | FR-SET-01 | Yes | Not started | Not started
PATCH | /me | Update profile, theme, prefs | FR-ONB-01, FR-SET | Yes | Not started | Not started
POST | /me/onboarding/complete | Finish onboarding, seed lists | FR-ONB-02 | Yes | Not started | Not started
DELETE | /me | Delete account | FR-SET-05 | Yes | Not started | Not started
POST | /me/devices | Register push token | FR-NOTIF-01 | Yes | Not started | Not started
GET | /dashboard | Dashboard payload | FR-DASH | Yes | Not started | Not started
GET | /cases | List / search / filter cases | FR-CASE-07..10 | Yes | Not started | Not started
POST | /cases | Create case | FR-CASE-01..06 | Yes | Not started | Not started
GET | /cases/:id | Case detail | FR-CASE-11 | Yes | Not started | Not started
PATCH | /cases/:id | Edit case | FR-CASE-11 | Yes | Not started | Not started
PATCH | /cases/:id/status | Change status | FR-CASE-13 | Yes | Not started | Not started
POST | /cases/:id/archive | Archive / unarchive | FR-CASE-14 | Yes | Not started | Not started
DELETE | /cases/:id | Soft delete | FR-CASE-15 | Yes | Not started | Not started
GET | /cases/:id/hearings | Hearing timeline | FR-HEAR-06 | Yes | Not started | Not started
POST | /cases/:id/hearings | Add hearing | FR-HEAR-01 | Yes | Not started | Not started
PATCH | /hearings/:id | Edit hearing | FR-HEAR-01 | Yes | Not started | Not started
POST | /hearings/:id/outcome | Outcome + next hearing (atomic) | FR-HEAR-02..05 | Yes | Not started | Not started
DELETE | /hearings/:id | Delete hearing | FR-HEAR-01 | Yes | Not started | Not started
GET | /hearings | Range query for calendar/today | FR-CAL | Yes | Not started | Not started
GET | /clients | List / search clients | FR-CLI-01 | Yes | Not started | Not started
POST | /clients | Create client | FR-CLI-01..02 | Yes | Not started | Not started
GET | /clients/:id | Client + linked cases | FR-CLI-04 | Yes | Not started | Not started
PATCH | /clients/:id | Edit client | FR-CLI-01 | Yes | Not started | Not started
DELETE | /clients/:id | Delete (409 if active cases) | FR-CLI-06 | Yes | Not started | Not started
GET/POST/PATCH | /courts | Manage courts | FR-SET-03 | Yes | Not started | Not started
GET/POST/PATCH | /case-types | Manage case types | FR-SET-03 | Yes | Not started | Not started
GET | /notifications | Notification list | FR-NOTIF-05 | Yes | Not started | Not started
POST | /notifications/read | Mark read | FR-NOTIF-05 | Yes | Not started | Not started
GET | /search | Global search (P1) | FR-SRCH-01 | Yes | Not started | Not started
GET/POST | /cases/:id/notes | Notes (P1) | FR-NOTE | Yes | Not started | Not started
PATCH/DELETE | /notes/:id | Edit/delete note (P1) | FR-NOTE | Yes | Not started | Not started
POST | /cases/:id/documents/upload-url | Signed upload URL (P1) | FR-DOC-01 | Yes | Not started | Not started
POST | /cases/:id/documents | Save doc metadata (P1) | FR-DOC-01 | Yes | Not started | Not started
GET | /cases/:id/documents | List docs (P1) | FR-DOC-02 | Yes | Not started | Not started
GET | /documents/:id/url | Signed download URL (P1) | FR-DOC-03 | Yes | Not started | Not started
PATCH/DELETE | /documents/:id | Rename/delete doc (P1) | FR-DOC-03 | Yes | Not started | Not started
GET/PUT | /cases/:id/fee | Agreed fee + summary (P1) | FR-FEE-01 | Yes | Not started | Not started
POST | /cases/:id/payments | Add payment (P1) | FR-FEE-02 | Yes | Not started | Not started
PATCH/DELETE | /payments/:id | Edit/delete payment (P1) | FR-FEE-02 | Yes | Not started | Not started
GET/POST | /tasks | Tasks (P1) | FR-TASK | Yes | Not started | Not started
PATCH/DELETE | /tasks/:id | Edit/delete task (P1) | FR-TASK | Yes | Not started | Not started

## Database
Supabase schema
Postgres. Every table also has id uuid PK, advocate_id, created_at, updated_at.
Table | Column(s) | Type | Constraint / values | Notes | Migration status
advocates | id | uuid | PK, = auth.users.id | The only entity | Not started
advocates | full_name / phone / email | text |  |  | Not started
advocates | enrolment_no | text | nullable | Bar Council enrolment | Not started
advocates | practice_areas | text[] |  |  | Not started
advocates | theme | text | dark ¦ light ¦ system, default dark |  | Not started
advocates | notification_prefs | jsonb |  | evening/morning times, toggles | Not started
advocates | onboarded_at | timestamptz | nullable |  | Not started
courts | name, short_name, city, district, state | text |  | Seeded per advocate | Not started
courts | sort_order / is_hidden | int / bool |  |  | Not started
case_types | name, sort_order, is_hidden | text / int / bool |  | Seeded, editable | Not started
clients | full_name, phone, alt_phone, email, address, notes | text | unique (advocate_id, phone) |  | Not started
cases | title, case_number, case_year, cnr_number | text / int | cnr 16 chars |  | Not started
cases | case_type_id, court_id | uuid | FK |  | Not started
cases | court_room, judge_name, filing_date | text / date |  |  | Not started
cases | our_side | text | petitioner ¦ respondent ¦ complainant ¦ accused ¦ appellant ¦ other |  | Not started
cases | petitioner_name, respondent_name, opposite_counsel | text |  |  | Not started
cases | stage | text |  |  | Not started
cases | status | text | active ¦ reserved ¦ disposed ¦ closed |  | Not started
cases | disposal_date, disposal_result | date / text |  |  | Not started
cases | priority | text | normal ¦ high ¦ urgent |  | Not started
cases | next_hearing_at, last_hearing_at | date | denormalized, indexed | Maintained by trigger/API | Not started
cases | archived_at, deleted_at | timestamptz |  | Soft flags | Not started
case_clients | case_id, client_id, role | uuid / text | PK (case_id, client_id) | Many-to-many | Not started
hearings | case_id, hearing_date, hearing_time | uuid / date / time | index (advocate_id, hearing_date) |  | Not started
hearings | purpose, court_room | text |  |  | Not started
hearings | outcome | text | adjourned ¦ heard ¦ arguments_done ¦ evidence ¦ reserved ¦ disposed ¦ not_reached ¦ other |  | Not started
hearings | outcome_notes, next_hearing_id, completed_at | text / uuid / timestamptz |  |  | Not started
notes | case_id, title, body, is_pinned, deleted_at |  |  | P1 | Not started
documents | case_id, file_name, category, mime_type, size_bytes, storage_path |  |  | P1, bucket case-docs | Not started
fees | case_id, agreed_amount | uuid / numeric(12,2) | one per case | P1 | Not started
payments | case_id, amount, paid_on, mode, note | numeric / date / text | mode: cash ¦ upi ¦ bank ¦ cheque | P1 | Not started
tasks | case_id, title, due_date, completed_at |  | case_id nullable | P1 | Not started
notifications | type, title, body, deep_link, read_at, sent_at |  | 60-day retention |  | Not started
device_tokens | expo_push_token, platform, last_seen_at | text |  |  | Not started
ALL TABLES | advocate_id, created_at, updated_at | uuid / timestamptz | RLS: advocate_id = auth.uid() | Every table | Not started

## Design Tokens
Design tokens
Column C/D: dark value / light value for semantic tokens; start / end stops for gradients. Swatches are filled.
Group | Token | Value (dark / start) | Value (light / end) | Notes
Primary | blue-50 | #EEF4FF
Primary | blue-100 | #DCE7FF
Primary | blue-200 | #BCD2FF
Primary | blue-300 | #8EB3FF
Primary | blue-400 | #5B8CFF
Primary | blue-500 | #3366FF |  | Dark primary
Primary | blue-600 | #2350E6 |  | Light primary
Primary | blue-700 | #1C3FC0
Primary | blue-800 | #1B3699
Primary | blue-900 | #1B3279
Primary | blue-950 | #121F4A
Neutral | ink-0 | #FFFFFF
Neutral | ink-50 | #F6F8FC
Neutral | ink-100 | #EDF1F8
Neutral | ink-200 | #DCE3EF
Neutral | ink-300 | #BCC7DA
Neutral | ink-400 | #8C9AB3
Neutral | ink-500 | #64728C
Neutral | ink-600 | #475570
Neutral | ink-700 | #2E3A52
Neutral | ink-800 | #1C2538
Neutral | ink-900 | #121A2B
Neutral | ink-950 | #0A101D
Semantic | bg | #0A101D | #F6F8FC
Semantic | surface | #121A2B | #FFFFFF
Semantic | surface-2 | #1C2538 | #EDF1F8
Semantic | border | #2E3A52 | #DCE3EF
Semantic | border-strong | #475570 | #BCC7DA
Semantic | text | #F6F8FC | #121A2B
Semantic | text-2 | #BCC7DA | #475570
Semantic | text-3 | #8C9AB3 | #64728C
Semantic | primary | #3366FF | #2350E6
Semantic | primary-pressed | #2350E6 | #1C3FC0
Semantic | primary-subtle | #121F4A | #EEF4FF
Status | success | #22C55E |  | bg dark #0F2A1C / light #E8F8EE
Status | warning | #F59E0B |  | bg dark #2E2209 / light #FEF4E2
Status | error | #EF4444 |  | bg dark #2F1316 / light #FDECEC
Status | info | #0EA5E9 |  | bg dark #0B2533 / light #E6F6FD
Status | adjourned | #8B5CF6 |  | bg dark #221A3D / light #F1ECFE
Gradient | grad-primary | #3366FF | #6A4CFF | 135 deg
Gradient | grad-hero | #1C3FC0 | #4FA3FF | 135 deg, mid #3366FF
Gradient | grad-success | #16A34A | #22C55E | 135 deg